## Sheet1
| Semester 1 | [13 empty] | Semester 2
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | Break | 12 | Exams | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Break | 8 | 9
Technical research
Technical learning
Gather source codes
API Integrations
Machine & Deep learning + Data gathering
Report: Intro
Jan Deliverable
Test deep learning
Improvements and additional functionality
Report: Technical
Further testing and evaluation
Report: Evaluation + Performance
Project submission